## WBSV10_1 IN_E_FIS_Codes
Updated 01/19/2011 |  | Appendix D of the "Guide to Project Delivery Workplan Standards", Release 10.1, August , 2009 entitled
Complete List of All WBS Elements Showing Proper Timesheet Coding
WBS Code | Phase | WBS Description | EFIS_SUBOBJ | EFIS_ACTIVITY | EFIS_SUBACT
0.100.05 | k | PROJECT MANAGEMENT - PID COMPONENT | 100 | 05
0.100.05.05 | k | PROJECT INITIATION AND PLANNING | 100 | 0505
0.100.05.10 | k | PID COMPONENT EXECUTION AND CONTROL | 100 | 0510
0.100.05.15 | k | PID COMPONENT CLOSE OUT | 100 | 0515
0.100.05.20 | k | PROJECT SHELVING [PID] | 100 | 0520
0.100.05.25 | k | PROJECT UNSHELVING [PID] | 100 | 0525
0.100.05.35 | k | EXECUTED COOPERATIVE AGREEMENT FOR PID PROCESS | 100 | 0535
0.100.05.99 | k | OTHER PROJECT MANAGEMENT PID PRODUCTS | 100 | 0599
0.100.10 | 0 | PROJECT MANAGEMENT - PA & ED COMPONENT | 100 | 10
0.100.10.05 | 0 | PA&ED COMPONENT INITIATION AND PLANNING | 100 | 1005
0.100.10.10 | 0 | PA&ED COMPONENT EXECUTION AND CONTROL | 100 | 1010
0.100.10.15 | 0 | PA&ED COMPONENT CLOSE OUT | 100 | 1015
0.100.10.20 | 0 | PROJECT SHELVING [PA&ED] | 100 | 1020
0.100.10.25 | 0 | PROJECT UNSHELVING [PA&ED] | 100 | 1025
0.100.10.30 | 0 | UPDATED ADMINISTRATIVE RECORD AND SUPPORT FOR LEGAL CHALLENGES DURING PA&ED | 100 | 1030
0.100.10.35 | 0 | EXECUTED COOPERATIVE AGREEMENT FOR PA&ED PROCESS | 100 | 1035
0.100.10.99 | 0 | OTHER PROJECT MANAGEMENT PA&ED PRODUCTS | 100 | 1099
0.100.15 | 1 | PROJECT MANAGEMENT - PS&E COMPONENT | 100 | 15
0.100.15.05 | 1 | PS&E COMPONENT INITIATION AND PLANNING | 100 | 1505
0.100.15.10 | 1 | PS&E COMPONENT EXECUTION AND CONTROL | 100 | 1510
0.100.15.15 | 1 | PS&E COMPONENT CLOSE OUT | 100 | 1515
0.100.15.20 | 1 | PROJECT SHELVING [PS&E] | 100 | 1520
0.100.15.25 | 1 | PROJECT UNSHELVING [PS&E] | 100 | 1525
0.100.15.30 | 1 | UPDATED ADMINISTRATIVE RECORD AND SUPPORT FOR LEGAL CHALLENGES DURING PS&E | 100 | 1530
0.100.15.35 | 1 | EXECUTED COOPERATIVE AGREEMENT FOR PS&E | 100 | 1535
0.100.15.99 | 1 | OTHER PROJECT MANAGEMENT PS&E PRODUCTS | 100 | 1599
0.100.20 | 3 | PROJECT MANAGEMENT - CONSTRUCTION COMPONENT | 100 | 20
0.100.20.05 | 3 | CONSTRUCTION COMPONENT INITIATION AND PLANNING | 100 | 2005
0.100.20.10 | 3 | CONSTRUCTION COMPONENT EXECUTION AND CONTROL | 100 | 2010
0.100.20.15 | 3 | CONSTRUCTION COMPONENT CLOSE OUT | 100 | 2015
0.100.20.20 | 3 | PROJECT SHELVING [CONSTRUCTION] | 100 | 2020
0.100.20.25 | 3 | PROJECT UNSHELVING [CONSTRUCTION] | 100 | 2025
0.100.20.30 | 3 | UPDATED ADMINISTRATIVE RECORD AND SUPPORT FOR LEGAL CHALLENGES DURING CONSTRUCTION | 100 | 2030
0.100.20.35 | 3 | EXECUTED COOPERATIVE AGREEMENT FOR CONSTRUCTION | 100 | 2035
0.100.20.99 | 3 | OTHER PROJECT MANAGEMENT CONSTRUCTION PRODUCTS | 100 | 2099
0.100.25 | 2 | PROJECT MANAGEMENT - RIGHT OF WAY COMPONENT | 100 | 25
0.100.25.05 | 2 | RIGHT OF WAY COMPONENT INITIATION AND PLANNING | 100 | 2505
0.100.25.10 | 2 | RIGHT OF WAY COMPONENT EXECUTION AND CONTROL | 100 | 2510
0.100.25.15 | 2 | RIGHT OF WAY COMPONENT CLOSE OUT | 100 | 2515
0.100.25.20 | 2 | PROJECT SHELVING [RIGHT OF WAY] | 100 | 2520
0.100.25.25 | 2 | PROJECT UNSHELVING [RIGHT OF WAY] | 100 | 2525
0.100.25.30 | 2 | UPDATED ADMINISTRATIVE RECORD AND SUPPORT FOR LEGAL CHALLENGES DURING RIGHT OF WAY | 100 | 2530
0.100.25.35 | 2 | EXECUTED COOPERATIVE AGREEMENT FOR R/W | 100 | 2535
0.100.25.50 | 2 | EXECUTED COOPERATIVE AGREEMENT FOR R/W RELINQUISHMENT | 100 | 2550
0.100.25.99 | 2 | OTHER PROJECT MANAGEMENT R/W PRODUCTS | 100 | 2599
1.150 | k | DEVELOP PROJECT INITIATION DOCUMENT [PID] | 150
1.150.05 | k | TRANSPORTATION PROBLEM DEFINITION AND SITE ASSESSMENT | 150 | 05
1.150.05.05 | k | REVIEW OF EXISTING REPORTS STUDIES AND MAPPING | 150 | 0505
1.150.05.10 | k | GEOLOGICAL HAZARDS REVIEW | 150 | 0510
1.150.05.15 | k | UTILITY SEARCH | 150 | 0515
1.150.05.20 | k | ENVIRONMENTAL CONSTRAINTS IDENTIFICATION | 150 | 0520
1.150.05.25 | k | TRAFFIC FORECASTS/MODELING | 150 | 0525
1.150.05.30 | k | SURVEYS AND MAPS FOR PID | 150 | 0530
1.150.05.30.05 | k | REGULAR SURVEYS AND MAPS FOR PID | 150 | 0530 | 05
1.150.05.30.10 | k | ACCELERATED ENGINEERING SURVEYS | 150 | 0530 | 10
1.150.05.35 | k | PROBLEM DEFINITION | 150 | 0535
1.150.05.45 | k | AS-BUILT CENTERLINE AND EXISTING RIGHT OF WAY | 150 | 0545
1.150.05.99 | k | OTHER DEFINITION AND ASSESSMENT PRODUCTS | 150 | 0599
1.150.10 | k | INITIAL ALTERNATIVES DEVELOPMENT | 150 | 10
1.150.10.05 | k | PUBLIC / LOCAL AGENCY INPUT | 150 | 1005
1.150.10.10 | k | VALUE ANALYSIS | 150 | 1010
1.150.10.15 | k | CONCEPT ALTERNATIVES DEVELOPMENT | 150 | 1015
1.150.10.99 | k | OTHER INITIAL ALTERNATIVES DEVELOPMENT PRODUCTS | 150 | 1099
1.150.15 | k | ALTERNATIVES ANALYSIS | 150 | 15
1.150.15.05 | k | RIGHT OF WAY DATA SHEETS | 150 | 1505
1.150.15.10 | k | UTILITY RELOCATION REQUIREMENTS ASSESSMENT | 150 | 1510
1.150.15.15 | k | RAILROAD INVOLVEMENT DETERMINATION | 150 | 1515
1.150.15.20 | k | DISTRICT PRELIMINARY GEOTECHNICAL REPORT [DPGR] | 150 | 1520
1.150.15.25 | k | PRELIMINARY MATERIALS REPORT | 150 | 1525
1.150.15.30 | k | STRUCTURES ADVANCE PLANNING STUDY [APS] | 150 | 1530
1.150.15.35 | k | MULTIMODAL REVIEW | 150 | 1535
1.150.15.40 | k | HYDRAULIC REVIEW | 150 | 1540
1.150.15.45 | k | TRAFFIC CAPACITY ANALYSIS | 150 | 1545
1.150.15.50 | k | TRAFFIC STUDIES | 150 | 1550
1.150.15.55 | k | CONSTRUCTION ESTIMATES | 150 | 1555
1.150.15.60 | k | PRELIMINARY TRANSPORTATION MANAGEMENT PLAN | 150 | 1560
1.150.15.99 | k | OTHER ALTERNATIVES ANALYSIS PRODUCTS | 150 | 1599
1.150.20 | k | PRELIMINARY ENVIRONMENTAL ANALYSIS REPORT [PEAR] | 150 | 20
1.150.20.05 | k | INITIAL NOISE STUDY | 150 | 2005
1.150.20.10 | k | HAZARDOUS WASTE INITIAL SITE ASSESSMENTS/INVESTIGATIONS | 150 | 2010
1.150.20.15 | k | SCENIC RESOURCE AND LANDSCAPE ARCHITECTURE REVIEW | 150 | 2015
1.150.20.20 | k | INITIAL NEPA/404 COORDINATION | 150 | 2020
1.150.20.25 | k | INITIAL BIOLOGY STUDY | 150 | 2025
1.150.20.30 | k | INITIAL RECORDS AND LITERATURE SEARCH FOR CULTURAL RESOURCES | 150 | 2030
1.150.20.40 | k | INITIAL COMMUNITY IMPACT ANALYSIS LAND USE AND GROWTH STUDIES | 150 | 2040
1.150.20.45 | k | INITIAL AIR QUALITY STUDY | 150 | 2045
1.150.20.50 | k | INITIAL WATER QUALITY STUDIES | 150 | 2050
1.150.20.55 | k | INITIAL FLOODPLAIN STUDY | 150 | 2055
1.150.20.60 | k | PEAR PREPARATION | 150 | 2060
1.150.20.65 | k | INITIAL PALEONTOLOGY STUDY | 150 | 2065
1.150.20.70 | k | INITIAL NATIVE AMERICAN COORDINATION | 150 | 2070
1.150.20.99 | k | OTHER PEAR PRODUCTS | 150 | 2099
1.150.25 | k | APPROVED PID [PSR PSSR ETC.] | 150 | 25
1.150.25.05 | k | DRAFT PID | 150 | 2505
1.150.25.10 | k | APPROVED EXCEPTIONS TO DESIGN STANDARDS DEVELOPMENT | 150 | 2510
1.150.25.15 | k | APPROVED ACCESS MODIFICATION REQUEST | 150 | 2515
1.150.25.20 | k | PID CIRCULATION REVIEW AND APPROVAL | 150 | 2520
1.150.25.25 | k | STORM WATER DATA REPORT | 150 | 2525
1.150.25.30 | k | DRAFT PROJECT REPORT AS PART OF A PSSR/PR PROGRAMMING DOCUMENT | 150 | 2530
1.150.25.30.05 | k | COST ESTIMATES FOR ALTERNATIVES | 150 | 2530 | 05
1.150.25.30.10 | k | FACT SHEET FOR EXCEPTIONS TO DESIGN STANDARDS | 150 | 2530 | 10
1.150.25.30.15 | k | APPROVED EXCEPTIONS TO ENCROACHMENT POLICY | 150 | 2530 | 15
1.150.25.30.20 | k | DRAFT PROJECT REPORT AS PART OF A PSSR/PR PROGRAMMING DOCUMENT | 150 | 2530 | 20
1.150.25.30.25 | k | DRAFT PROJECT REPORT CIRCULATION REVIEW & APPROVAL | 150 | 2530 | 25
1.150.25.99 | k | OTHER APPROVED PID PRODUCTS | 150 | 2599
1.150.35 | k | REQUIRED PERMITS DURING PROJECT INITIATION DOCUMENTS DEVELOPMENT | 150 | 35
1.150.40 | k | PERMITS DURING PROJECT INITIATION DOCUMENTS DEVELOPMENT | 150 | 40
1.150.40.05 | k | U.S. ARMY CORPS OF ENGINEERS PERMIT [404] | 150 | 4005
1.150.40.10 | k | U.S. FOREST SERVICE PERMIT[S] | 150 | 4010
1.150.40.15 | k | U.S. COAST GUARD PERMIT | 150 | 4015
1.150.40.20 | k | DEPARTMENT OF FISH AND GAME 1600 AGREEMENT[S] | 150 | 4020
1.150.40.25 | k | COASTAL ZONE DEVELOPMENT PERMIT | 150 | 4025
1.150.40.30 | k | LOCAL AGENCY CONCURRENCE/PERMIT | 150 | 4030
1.150.40.35 | k | WASTE DISCHARGE [NPDES] PERMIT[S] | 150 | 4035
1.150.40.40 | k | U.S. FISH AND WILDLIFE SERVICE APPROVAL | 150 | 4040
1.150.40.45 | k | REGIONAL WATER QUALITY CONTROL BOARD 401 PERMIT | 150 | 4045
1.150.40.50 | k | ENVIRONMENTAL COMMITMENTS RECORD | 150 | 4050
1.150.40.55 | k | NEPA DELEGATION | 150 | 4055
1.150.40.95 | k | OTHER PERMITS | 150 | 4095
1.150.45 | k | BASE MAPS AND PLAN SHEETS FOR PROJECT INITIATION DOCUMENTS | 150 | 45
2.160 | 0 | PERFORM PRELIMINARY ENGINEERING STUDIES AND DRAFT PROJECT REPORT | 160
2.160.05 | 0 | UPDATED PROJECT INFORMATION | 160 | 05
2.160.05.05 | 0 | APPROVED PID REVIEW | 160 | 0505
2.160.05.10 | 0 | GEOTECHNICAL INFORMATION REVIEW | 160 | 0510
2.160.05.15 | 0 | MATERIALS INFORMATION REVIEW | 160 | 0515
2.160.05.20 | 0 | TRAFFIC DATA AND FORECASTS REVIEW | 160 | 0520
2.160.05.25 | 0 | GEOMETRICS REVIEW | 160 | 0525
2.160.05.30 | 0 | PROJECT SCOPE REVIEW | 160 | 0530
2.160.05.35 | 0 | PROJECT COST ESTIMATE REVIEW | 160 | 0535
2.160.05.99 | 0 | OTHER UPDATED PROJECT INFORMATION PRODUCTS | 160 | 0599
2.160.10 | 0 | ENGINEERING STUDIES | 160 | 10
2.160.10.10 | 0 | TRAFFIC FORECASTS/MODELING | 160 | 1010
2.160.10.15 | 0 | GEOMETRIC PLANS FOR PROJECT ALTERNATIVES | 160 | 1015
2.160.10.20 | 0 | VALUE ANALYSIS | 160 | 1020
2.160.10.25 | 0 | HYDRAULICS/HYDROLOGY STUDIES | 160 | 1025
2.160.10.30 | 0 | HIGHWAY PLANTING DESIGN CONCEPTS | 160 | 1030
2.160.10.35 | 0 | TRAFFIC OPERATIONAL ANALYSIS | 160 | 1035
2.160.10.40 | 0 | UPDATED RIGHT OF WAY DATA SHEET | 160 | 1040
2.160.10.45 | 0 | UTILITY LOCATIONS DETERMINED FOR PRELIMINARY ENGINEERING | 160 | 1045
2.160.10.50 | 0 | RAILROAD STUDY | 160 | 1050
2.160.10.55 | 0 | MULTI-MODAL STUDY | 160 | 1055
2.160.10.60 | 0 | PARK & RIDE STUDY | 160 | 1060
2.160.10.65 | 0 | RIGHT OF WAY RELINQUISHMENT AND VACATION STUDY | 160 | 1065
2.160.10.70 | 0 | TRAFFIC STUDIES | 160 | 1070
2.160.10.75 | 0 | UPDATED MATERIALS INFORMATION | 160 | 1075
2.160.10.80 | 0 | UPDATED GEOTECHNICAL INFORMATION | 160 | 1080
2.160.10.85 | 0 | STRUCTURES ADVANCE PLANNING STUDY [APS] AND PRELIMINARY ENGINEERING | 160 | 1085
2.160.10.90 | 0 | HIGH OCCUPANCY VEHICLE REPORT | 160 | 1090
2.160.10.95 | 0 | UPDATED PRELIMINARY TRANSPORTATION MANAGEMENT PLAN | 160 | 1095
2.160.10.99 | 0 | OTHER ENGINEERING STUDIES | 160 | 1099
2.160.15 | 0 | DRAFT PROJECT REPORT | 160 | 15
2.160.15.05 | 0 | COST ESTIMATES FOR ALTERNATIVES | 160 | 1505
2.160.15.10 | 0 | FACT SHEET FOR EXCEPTIONS TO DESIGN STANDARDS | 160 | 1510
2.160.15.15 | 0 | APPROVED EXCEPTIONS TO ENCROACHMENT POLICY | 160 | 1515
2.160.15.20 | 0 | DRAFT PROJECT REPORT | 160 | 1520
2.160.15.25 | 0 | DRAFT PROJECT REPORT CIRCULATION REVIEW & APPROVAL | 160 | 1525
2.160.15.99 | 0 | OTHER DRAFT PROJECT REPORT PRODUCTS | 160 | 1599
2.160.20 | 0 | ENGINEERING AND LAND NET SURVEYS | 160 | 20
2.160.20.25 | 0 | EXISTING RECORDS | 160 | 2025
2.160.20.30 | 0 | LAND NET SURVEYS | 160 | 2030
2.160.20.35 | 0 | LAND NET MAP | 160 | 2035
2.160.20.40 | 0 | RIGHT OF WAY ENGINEERING PRODUCTS | 160 | 2040
2.160.20.50 | 0 | CONTROL SURVEYS | 160 | 2050
2.160.20.55 | 0 | PHOTOGRAMMETRIC MAPS AND PRODUCTS | 160 | 2055
2.160.20.60 | 0 | ENGINEERING SURVEYS | 160 | 2060
2.160.20.65 | 0 | AS-BUILT CENTERLINE SURVEYS | 160 | 2065
2.160.20.70 | 0 | PAVEMENT SURVEYS | 160 | 2070
2.160.30 | 0 | ENVIRONMENTAL STUDY REQUEST [ESR] | 160 | 30
2.160.30.05 | 0 | MAPS FOR ESR | 160 | 3005
2.160.30.10 | 0 | SURVEYS AND MAPPING FOR ENVIRONMENTAL STUDIES | 160 | 3010
2.160.30.15 | 0 | PROPERTY ACCESS RIGHTS FOR ENVIRONMENTAL/ENGINEERING STUDIES | 160 | 3015
2.160.40 | 0 | NEPA DELEGATION | 160 | 40
2.160.45 | 0 | BASE MAPS AND PLAN SHEETS FOR PA&ED DEVELOPMENT | 160 | 45
2.165 | 0 | PERFORM ENVIRONMENTAL STUDIES AND PREPARE DRAFT ENVIRONMENTAL DOCUMENT | 165
2.165.05 | 0 | ENVIRONMENTAL SCOPING OF ALTERNATIVES IDENTIFIED FOR STUDIES IN THE PID | 165 | 05
2.165.05.05 | 0 | PROJECT INFORMATION REVIEW | 165 | 0505
2.165.05.10 | 0 | PUBLIC AND AGENCY SCOPING PROCESS | 165 | 0510
2.165.05.15 | 0 | ALTERNATIVES FOR FURTHER STUDY | 165 | 0515
2.165.05.99 | 0 | OTHER ENVIRONMENTAL SCOPING OF ALTERNATIVES IDENTIFIED FOR STUDIES IN PID | 165 | 0599
2.165.10 | 0 | GENERAL ENVIRONMENTAL STUDIES | 165 | 10
2.165.10.15 | 0 | COMMUNITY IMPACT ANALYSIS LAND USE AND GROWTH STUDIES | 165 | 1015
2.165.10.20 | 0 | VISUAL IMPACT ASSESSMENT AND SCENIC RESOURCE EVALUATION | 165 | 1020
2.165.10.25 | 0 | NOISE STUDY | 165 | 1025
2.165.10.30 | 0 | AIR QUALITY STUDY | 165 | 1030
2.165.10.35 | 0 | WATER QUALITY STUDIES | 165 | 1035
2.165.10.40 | 0 | ENERGY STUDIES | 165 | 1040
2.165.10.45 | 0 | SUMMARY OF GEOTECHNICAL REPORT | 165 | 1045
2.165.10.55 | 0 | DRAFT RIGHT OF WAY RELOCATION IMPACT DOCUMENT | 165 | 1055
2.165.10.60 | 0 | LOCATION HYDRAULIC & FLOODPLAIN STUDY REPORTS | 165 | 1060
2.165.10.65 | 0 | PALEONTOLOGY STUDY | 165 | 1065
2.165.10.70 | 0 | WILD AND SCENIC RIVERS COORDINATION | 165 | 1070
2.165.10.75 | 0 | ENVIRONMENTAL COMMITMENTS RECORD | 165 | 1075
2.165.10.80 | 0 | HAZARDOUS WASTE INITIAL SITE ASSESSMENTS/INVESTIGATIONS | 165 | 1080
2.165.10.85 | 0 | HAZARDOUS WASTE PRELIMINARY SITE INVESTIGATIONS | 165 | 1085
2.165.10.99 | 0 | OTHER ENVIRONMENTAL STUDIES | 165 | 1099
2.165.15 | 0 | BIOLOGICAL STUDIES | 165 | 15
2.165.15.05 | 0 | BIOLOGICAL ASSESSMENT | 165 | 1505
2.165.15.10 | 0 | WETLANDS STUDY | 165 | 1510
2.165.15.15 | 0 | RESOURCE AGENCY PERMIT RELATED COORDINATION | 165 | 1515
2.165.15.20 | 0 | NATURAL ENVIRONMENT STUDY [NES] REPORT | 165 | 1520
2.165.15.99 | 0 | OTHER BIOLOGICAL STUDIES | 165 | 1599
2.165.20 | 0 | CULTURAL RESOURCE STUDIES | 165 | 20
2.165.20.05 | 0 | ARCHAEOLOGICAL SURVEY | 165 | 2005
2.165.20.05.05 | 0 | AREA OF POTENTIAL EFFECTS/STUDY AREA MAPS | 165 | 2005 | 05
2.165.20.05.10 | 0 | NATIVE AMERICAN CONSULTATION | 165 | 2005 | 10
2.165.20.05.15 | 0 | RECORDS AND LITERATURE SEARCH | 165 | 2005 | 15
2.165.20.05.20 | 0 | FIELD SURVEY | 165 | 2005 | 20
2.165.20.05.25 | 0 | ARCHAEOLOGICAL SURVEY REPORT [ASR] | 165 | 2005 | 25
2.165.20.05.99 | 0 | OTHER ARCHAEOLOGICAL SURVEY PRODUCTS | 165 | 2005 | 99
2.165.20.10 | 0 | EXTENDED PHASE I ARCHAEOLOGICAL STUDIES | 165 | 2010
2.165.20.10.05 | 0 | NATIVE AMERICAN CONSULTATION | 165 | 2010 | 05
2.165.20.10.10 | 0 | EXTENDED PHASE 1 PROPOSAL | 165 | 2010 | 10
2.165.20.10.15 | 0 | EXTENDED PHASE I FIELD INVESTIGATION | 165 | 2010 | 15
2.165.20.10.20 | 0 | EXTENDED PHASE I MATERIALS ANALYSIS | 165 | 2010 | 20
2.165.20.10.25 | 0 | EXTENDED PHASE I REPORT | 165 | 2010 | 25
2.165.20.10.99 | 0 | OTHER EXTENDED PHASE I ARCHAEOLOGICAL STUDY PRODUCTS | 165 | 2010 | 99
2.165.20.15 | 0 | PHASE II ARCHAEOLOGICAL STUDIES | 165 | 2015
2.165.20.15.05 | 0 | NATIVE AMERICAN CONSULTATION | 165 | 2015 | 05
2.165.20.15.10 | 0 | PHASE II PROPOSAL | 165 | 2015 | 10
2.165.20.15.15 | 0 | PHASE II FIELD INVESTIGATION | 165 | 2015 | 15
2.165.20.15.20 | 0 | PHASE II MATERIALS ANALYSIS | 165 | 2015 | 20
2.165.20.15.25 | 0 | PHASE II REPORT | 165 | 2015 | 25
2.165.20.15.99 | 0 | OTHER EXTENDED PHASE II ARCHAEOLOGICAL STUDY PRODUCTS | 165 | 2015 | 99
2.165.20.20 | 0 | HISTORICAL AND ARCHITECTURAL RESOURCE STUDIES | 165 | 2020
2.165.20.20.05 | 0 | PRELIMINARY AREA OF POTENTIAL EFFECTS/STUDY AREA MAPS FOR ARCHITECTURE | 165 | 2020 | 05
2.165.20.20.10 | 0 | HISTORIC RESOURCE EVALUATION REPORTS - ARCHAEOLOGY | 165 | 2020 | 10
2.165.20.20.15 | 0 | HISTORIC RESOURCE EVALUATION REPORTS - ARCHITECTURE | 165 | 2020 | 15
2.165.20.20.20 | 0 | BRIDGE EVALUATION | 165 | 2020 | 20
2.165.20.20.99 | 0 | OTHER HISTORICAL AND ARCHITECTURAL RESOURCE STUDY PRODUCTS | 165 | 2020 | 99
2.165.20.25 | 0 | CULTURAL RESOURCE COMPLIANCE CONSULTATION DOCUMENTS | 165 | 2025
2.165.20.25.05 | 0 | FINAL AREA OF POTENTIAL EFFECTS/STUDY AREA MAPS | 165 | 2025 | 05
2.165.20.25.10 | 0 | PRC 5024.5 CONSULTATION | 165 | 2025 | 10
2.165.20.25.15 | 0 | HISTORIC PROPERTY SURVEY REPORTS / HISTORIC RESOURCE COMPLIANCE REPORTS | 165 | 2025 | 15
2.165.20.25.20 | 0 | FINDING OF EFFECT [FOE] | 165 | 2025 | 20
2.165.20.25.25 | 0 | ARCHAEOLOGICAL DATA RECOVERY PLAN/TREATMENT PLAN | 165 | 2025 | 25
2.165.20.25.30 | 0 | MEMORANDUM OF AGREEMENT [MOA] | 165 | 2025 | 30
2.165.20.25.99 | 0 | OTHER CULTURAL RESOURCE COMPLIANCE CONSULTATION PRODUCTS | 165 | 2025 | 99
2.165.25 | 0 | DRAFT ENVIRONMENTAL DOCUMENT | 165 | 25
2.165.25.05 | 0 | DRAFT ENVIRONMENTAL DOCUMENT ANALYSIS | 165 | 2505
2.165.25.10 | 0 | SECTION 4[F] EVALUATION | 165 | 2510
2.165.25.15 | 0 | CATEGORICAL EXEMPTION / CATEGORICAL EXCLUSION [CE] DETERMINATION | 165 | 2515
2.165.25.20 | 0 | ENVIRONMENTAL QUALITY CONTROL & OTHER REVIEWS | 165 | 2520
2.165.25.25 | 0 | APPROVAL TO CIRCULATE RESOLUTION | 165 | 2525
2.165.25.30 | 0 | ENVIRONMENTAL COORDINATION | 165 | 2530
2.165.25.99 | 0 | OTHER DRAFT ENVIRONMENTAL DOCUMENT PRODUCTS | 165 | 2599
2.165.30 | 0 | NEPA DELEGATION | 165 | 30
2.170 | 0 | PERMITS AGREEMENTS AND ROUTE ADOPTIONS DURING PA&ED COMPONENT | 170
2.170.05 | 0 | REQUIRED PERMITS | 170 | 05
2.170.10 | 0 | PERMITS | 170 | 10
2.170.10.05 | 0 | U.S. ARMY CORPS OF ENGINEERS PERMIT [404] | 170 | 1005
2.170.10.10 | 0 | U.S. FOREST SERVICE PERMIT[S] | 170 | 1010
2.170.10.15 | 0 | U.S. COAST GUARD PERMIT | 170 | 1015
2.170.10.20 | 0 | DEPARTMENT OF FISH AND GAME 1600 AGREEMENT[S] | 170 | 1020
2.170.10.25 | 0 | COASTAL ZONE DEVELOPMENT PERMIT | 170 | 1025
2.170.10.30 | 0 | LOCAL AGENCY CONCURRENCE/PERMIT | 170 | 1030
2.170.10.40 | 0 | WASTE DISCHARGE [NPDES] PERMIT[S] | 170 | 1040
2.170.10.45 | 0 | U.S. FISH AND WILDLIFE SERVICE APPROVAL | 170 | 1045
2.170.10.50 | 0 | REGIONAL WATER QUALITY CONTROL BOARD 401 PERMIT | 170 | 1050
2.170.10.60 | 0 | UPDATED ECR | 170 | 1060
2.170.10.95 | 0 | OTHER PERMITS | 170 | 1095
2.170.15 | 0 | RAILROAD AGREEMENTS | 170 | 15
2.170.15.05 | 0 | PLAN APPROVAL | 170 | 1505
2.170.15.10 | 0 | SPECIAL PROVISIONS AND INSURANCE CLAUSES | 170 | 1510
2.170.15.15 | 0 | SERVICE CONTRACT FOR RAILROAD SERVICES | 170 | 1515
2.170.15.20 | 0 | CONSTRUCTION AND MAINTENANCE AGREEMENT | 170 | 1520
2.170.15.25 | 0 | PUC EXHIBITS AND APPLICATION | 170 | 1525
2.170.15.99 | 0 | OTHER RAILROAD AGREEMENT PRODUCTS | 170 | 1599
2.170.20 | 0 | FREEWAY AGREEMENTS | 170 | 20
2.170.20.05 | 0 | DRAFT FREEWAY AGREEMENT | 170 | 2005
2.170.20.10 | 0 | DRAFT FREEWAY AGREEMENT REVIEW | 170 | 2010
2.170.20.15 | 0 | FINAL FREEWAY AGREEMENT | 170 | 2015
2.170.20.20 | 0 | EXECUTED FREEWAY AGREEMENT | 170 | 2020
2.170.20.99 | 0 | OTHER FREEWAY AGREEMENT PRODUCTS | 170 | 2099
2.170.25 | 0 | AGREEMENT FOR MATERIAL SITES | 170 | 25
2.170.30 | 0 | EXECUTED MAINTENANCE AGREEMENT | 170 | 30
2.170.40 | 0 | ROUTE ADOPTIONS | 170 | 40
2.170.40.05 | 0 | ROUTE ADOPTION MAP | 170 | 4005
2.170.40.10 | 0 | NEW CONNECTION REQUEST AND ROUTE ADOPTION CTC SUBMITTAL | 170 | 4010
2.170.40.15 | 0 | ROUTE ADOPTION AND PUBLIC ROAD CONNECTION PLACED ON CTC AGENDA | 170 | 4015
2.170.40.99 | 0 | OTHER ROUTE ADOPTION PRODUCTS | 170 | 4099
2.170.45 | 0 | MOU FROM TRIBAL EMPLOYMENT RIGHTS OFFICE [TERO] | 170 | 45
2.170.55 | 0 | NEPA DELEGATION | 170 | 55
2.175 | 0 | CIRCULATE DRAFT ENVIRONMENTAL DOCUMENT AND SELECT PREFERRED PROJECT ALTERNATIVE | 175
2.175.05 | 0 | DED CIRCULATION | 175 | 05
2.175.05.05 | 0 | MASTER DISTRIBUTION AND INVITATION LISTS | 175 | 0505
2.175.05.10 | 0 | NOTICES REGARDING PUBLIC HEARING & AVAILABILITY OF DRAFT ENVIRONMENTAL DOCUMENT | 175 | 0510
2.175.05.15 | 0 | DED PUBLICATION AND CIRCULATION | 175 | 0515
2.175.05.20 | 0 | FEDERAL CONSISTENCY DETERMINATION [COASTAL ZONE] | 175 | 0520
2.175.05.99 | 0 | OTHER DED CIRCULATION PRODUCTS | 175 | 0599
2.175.10 | 0 | PUBLIC HEARING | 175 | 10
2.175.10.05 | 0 | NEED FOR PUBLIC HEARING DETERMINATION | 175 | 1005
2.175.10.10 | 0 | PUBLIC HEARING LOGISTICS | 175 | 1010
2.175.10.15 | 0 | DISPLAYS FOR PUBLIC HEARING | 175 | 1015
2.175.10.20 | 0 | SECOND NOTICES OF PUBLIC HEARING AND AVAILABILITY OF DED | 175 | 1020
2.175.10.25 | 0 | MAP DISPLAY AND PUBLIC HEARING PLAN | 175 | 1025
2.175.10.30 | 0 | DISPLAY PUBLIC HEARING MAPS | 175 | 1030
2.175.10.35 | 0 | PUBLIC HEARING | 175 | 1035
2.175.10.40 | 0 | RECORD OF PUBLIC HEARING | 175 | 1040
2.175.10.99 | 0 | OTHER PUBLIC HEARING PRODUCTS | 175 | 1099
2.175.15 | 0 | PUBLIC COMMENT RESPONSES AND CORRESPONDENCE | 175 | 15
2.175.20 | 0 | PROJECT PREFERRED ALTERNATIVE | 175 | 20
2.175.25 | 0 | NEPA DELEGATION | 175 | 25
2.180 | 0 | PREPARE AND APPROVE PROJECT REPORT AND FINAL ENVIRONMENTAL DOCUMENT | 180
2.180.05 | 0 | FINAL PROJECT REPORT | 180 | 05
2.180.05.05 | 0 | UPDATED DRAFT PROJECT REPORT | 180 | 0505
2.180.05.10 | 0 | APPROVED PROJECT REPORT | 180 | 0510
2.180.05.15 | 0 | UPDATED STORM WATER DATA REPORT | 180 | 0515
2.180.05.99 | 0 | OTHER FINAL PROJECT REPORT PRODUCTS | 180 | 0599
2.180.10 | 0 | FINAL ENVIRONMENTAL DOCUMENT | 180 | 10
2.180.10.05 | 0 | APPROVED FINAL ENVIRONMENTAL DOCUMENT | 180 | 1005
2.180.10.05.05 | 0 | DRAFT FINAL ENVIRONMENTAL DOCUMENT REVIEW | 180 | 1005 | 05
2.180.10.05.10 | 0 | REVISED DRAFT FINAL ENVIRONMENTAL DOCUMENT | 180 | 1005 | 10
2.180.10.05.15 | 0 | SECTION 4[F] EVALUATION | 180 | 1005 | 15
2.180.10.05.20 | 0 | FINDINGS | 180 | 1005 | 20
2.180.10.05.25 | 0 | STATEMENT OF OVERRIDING CONSIDERATIONS | 180 | 1005 | 25
2.180.10.05.30 | 0 | CEQA CERTIFICATION | 180 | 1005 | 30
2.180.10.05.35 | 0 | FHWA APPROVAL | 180 | 1005 | 35
2.180.10.05.40 | 0 | SECTION 106 CONSULTATION AND MOA | 180 | 1005 | 40
2.180.10.05.45 | 0 | SECTION 7 CONSULTATION | 180 | 1005 | 45
2.180.10.05.50 | 0 | FINAL SECTION 4[F] STATEMENT | 180 | 1005 | 50
2.180.10.05.55 | 0 | FLOODPLAIN ONLY PRACTICABLE ALTERNATIVE FINDING | 180 | 1005 | 55
2.180.10.05.60 | 0 | WETLANDS ONLY PRACTICABLE ALTERNATIVE FINDING | 180 | 1005 | 60
2.180.10.05.65 | 0 | SECTION 404 COMPLIANCE | 180 | 1005 | 65
2.180.10.05.70 | 0 | MITIGATION MEASURES | 180 | 1005 | 70
2.180.10.10 | 0 | PUBLIC DISTRIBUTION OF FED AND RESPOND TO COMMENTS | 180 | 1010
2.180.10.15 | 0 | FINAL RIGHT OF WAY RELOCATION IMPACT DOCUMENT | 180 | 1015
2.180.10.99 | 0 | OTHER FED PRODUCTS | 180 | 1099
2.180.15 | 0 | COMPLETED ENVIRONMENTAL DOCUMENT | 180 | 15
2.180.15.05 | 0 | RECORD OF DECISION [NEPA] | 180 | 1505
2.180.15.10 | 0 | NOTICE OF DETERMINATION [CEQA] | 180 | 1510
2.180.15.20 | 0 | ENVIRONMENTAL COMMITMENTS RECORD | 180 | 1520
2.180.15.99 | 0 | OTHER COMPLETED ENVIRONMENTAL DOCUMENT PRODUCTS | 180 | 1599
2.180.20 | 0 | NEPA DELEGATION | 180 | 20
3.185 | 1 | PREPARE BASE MAPS AND PLAN SHEETS DURING PS&E DEVELOPMENT | 185
3.185.05 | 1 | UPDATED PROJECT INFORMATION | 185 | 05
3.185.05.05 | 1 | PROJECT CONCEPT REVIEW | 185 | 0505
3.185.05.10 | 1 | UPDATED PROJECT INFORMATION | 185 | 0510
3.185.05.99 | 1 | OTHER UPDATED PROJECT INFORMATION PRODUCTS | 185 | 0599
3.185.10 | 1 | ENGINEERING AND PHOTOGRAMMETRIC SURVEYS | 185 | 10
3.185.10.50 | 1 | CONTROL SURVEYS | 185 | 1050
3.185.10.55 | 1 | PHOTOGRAMMETRIC MAPS AND PRODUCTS | 185 | 1055
3.185.10.60 | 1 | ENGINEERING SURVEYS | 185 | 1060
3.185.10.65 | 1 | AS-BUILT CENTERLINE SURVEYS | 185 | 1065
3.185.10.70 | 1 | PAVEMENT SURVEYS | 185 | 1070
3.185.15 | 1 | PRELIMINARY DESIGN | 185 | 15
3.185.15.05 | 1 | ROADWAY AND MISCELLANEOUS DESIGN | 185 | 1505
3.185.15.10 | 1 | PROPOSED GEOMETRICS REVIEW | 185 | 1510
3.185.15.15 | 1 | REQUESTS FOR EXCEPTIONS TO DESIGN STANDARDS | 185 | 1515
3.185.15.20 | 1 | VALUE ANALYSIS | 185 | 1520
3.185.15.99 | 1 | OTHER PRELIMINARY DESIGN PRODUCTS | 185 | 1599
3.185.20 | 1 | ENGINEERING REPORTS | 185 | 20
3.185.20.05 | 1 | UPDATED TRAFFIC DATA ANALYSIS AND FORECASTS | 185 | 2005
3.185.20.10 | 1 | PRELIMINARY HYDROLOGY AND HYDRAULIC REPORTS | 185 | 2010
3.185.20.15 | 1 | PRELIMINARY GEOTECHNICAL DESIGN REPORT [PGDR] | 185 | 2015
3.185.20.20 | 1 | PRELIMINARY PAVEMENT DESIGN REPORT | 185 | 2020
3.185.20.25 | 1 | PRELIMINARY MATERIALS REPORT | 185 | 2025
3.185.20.30 | 1 | SOUNDWALL DESIGN REPORT | 185 | 2030
3.185.20.35 | 1 | UPDATED TRANSPORTATION MANAGEMENT PLAN FOR DESIGN PHASE | 185 | 2035
3.185.20.40 | 1 | UTILITY LOCATIONS DETERMINED FOR DESIGN | 185 | 2040
3.185.20.99 | 1 | OTHER ENGINEERING REPORTS PRODUCTS | 185 | 2099
3.185.25 | 1 | RIGHT OF WAY REQUIREMENTS DETERMINATION | 185 | 25
3.185.25.05 | 1 | PROJECT REVIEW WITH AFFECTED AGENCIES | 185 | 2505
3.185.25.10 | 1 | FEE AND EASEMENT REQUIREMENTS DETERMINATION | 185 | 2510
3.185.25.15 | 1 | RIGHT OF WAY REQUIREMENTS MAPS | 185 | 2515
3.185.25.20 | 1 | FINAL RAILROAD INVOLVEMENT DETERMINATION | 185 | 2520
3.185.25.25 | 1 | WATER WELL ABANDONMENT NEEDS DETERMINATION | 185 | 2525
3.185.25.30 | 1 | UTILITY CONFLICT MAPS | 185 | 2530
3.185.30 | 1 | STRUCTURE SITE PLANS | 185 | 30
3.185.30.10 | 1 | SITE PLANS FOR BRIDGES AND STRUCTURES | 185 | 3010
3.185.30.15 | 1 | SITE PLANS FOR RETAINING WALLS AND NON-STANDARD EARTH RETENTION SYSTEMS | 185 | 3015
3.185.30.20 | 1 | SITE PLANS FOR SOUNDWALLS ON RETAINING SYSTEMS OR STRUCTURES | 185 | 3020
3.185.30.25 | 1 | SITE PLANS FOR PUMPING PLANTS | 185 | 3025
3.185.30.30 | 1 | SITE PLANS FOR SPECIAL-DESIGN CULVERTS | 185 | 3030
3.185.30.99 | 1 | OTHER STRUCTURE SITE PLAN PRODUCTS | 185 | 3099
3.185.99 | 1 | OTHER BASE MAPS AND PLAN SHEETS PRODUCTS | 185 | 99
3.205 | 1 | PERMITS AND AGREEMENTS DURING PS&E COMPONENT | 205
3.205.05 | 1 | REQUIRED PERMITS | 205 | 05
3.205.10 | 1 | PERMITS | 205 | 10
3.205.10.05 | 1 | U.S. ARMY CORPS OF ENGINEERS PERMIT [404] | 205 | 1005
3.205.10.10 | 1 | U.S. FOREST SERVICE PERMIT[S] | 205 | 1010
3.205.10.15 | 1 | U.S. COAST GUARD PERMIT | 205 | 1015
3.205.10.20 | 1 | DEPARTMENT OF FISH AND GAME 1600 AGREEMENT[S] | 205 | 1020
3.205.10.25 | 1 | COASTAL ZONE DEVELOPMENT PERMIT | 205 | 1025
3.205.10.30 | 1 | LOCAL AGENCY CONCURRENCE/PERMIT | 205 | 1030
3.205.10.40 | 1 | WASTE DISCHARGE [NPDES] PERMIT[S] | 205 | 1040
3.205.10.45 | 1 | U.S. FISH AND WILDLIFE SERVICE APPROVAL | 205 | 1045
3.205.10.50 | 1 | REGIONAL WATER QUALITY CONTROL BOARD 401 PERMIT | 205 | 1050
3.205.10.60 | 1 | UPDATED ECR | 205 | 1060
3.205.10.95 | 1 | OTHER PERMITS | 205 | 1095
3.205.15 | 1 | RAILROAD AGREEMENTS | 205 | 15
3.205.15.05 | 1 | PLAN APPROVAL | 205 | 1505
3.205.15.10 | 1 | SPECIAL PROVISIONS AND INSURANCE CLAUSES | 205 | 1510
3.205.15.15 | 1 | SERVICE CONTRACT FOR RAILROAD SERVICES | 205 | 1515
3.205.15.20 | 1 | CONSTRUCTION AND MAINTENANCE AGREEMENT | 205 | 1520
3.205.15.25 | 1 | PUC EXHIBITS AND APPLICATION | 205 | 1525
3.205.15.99 | 1 | OTHER RAILROAD AGREEMENT PRODUCTS | 205 | 1599
3.205.25 | 1 | AGREEMENT FOR MATERIAL SITES | 205 | 25
3.205.30 | 1 | EXECUTED MAINTENANCE AGREEMENT | 205 | 30
3.205.45 | 1 | MOU FROM TRIBAL EMPLOYMENT RIGHTS OFFICE [TERO] | 205 | 45
3.205.55 | 1 | NEPA DELEGATION | 205 | 55
3.230 | 1 | PREPARE DRAFT PS&E | 230
3.230.05 | 1 | DRAFT ROADWAY PLANS | 230 | 05
3.230.05.05 | 1 | TITLE SHEET | 230 | 0505
3.230.05.10 | 1 | TYPICAL CROSS SECTIONS | 230 | 0510
3.230.05.15 | 1 | KEY MAP AND LINE INDEX | 230 | 0515
3.230.05.20 | 1 | ROADWAY LAYOUTS | 230 | 0520
3.230.05.25 | 1 | PROFILE AND SUPERELEVATION SHEETS | 230 | 0525
3.230.05.30 | 1 | CONSTRUCTION DETAILS | 230 | 0530
3.230.05.35 | 1 | CONTOUR GRADING PLANS | 230 | 0535
3.230.05.40 | 1 | SUMMARY OF QUANTITIES SHEETS | 230 | 0540
3.230.05.45 | 1 | NOISE BARRIER PLANS | 230 | 0545
3.230.05.50 | 1 | RETAINING WALL PLANS | 230 | 0550
3.230.05.55 | 1 | STANDARD PLANS SELECTION | 230 | 0555
3.230.05.60 | 1 | STAGE CONSTRUCTION AND DETOUR PLANS OR TRAFFIC HANDLING PLANS | 230 | 0560
3.230.05.65 | 1 | WATER POLLUTION CONTROL PLANS | 230 | 0565
3.230.05.70 | 1 | ENGINEERING REPORTS | 230 | 0570
3.230.05.70.05 | 1 | HYDROLOGY AND HYDRAULIC REPORTS | 230 | 0570 | 05
3.230.05.70.10 | 1 | PRODUCTS REQUIRED TO READY SITE FOR SUBSURFACE EXPLORATION | 230 | 0570 | 10
3.230.05.70.15 | 1 | GEOTECHNICAL DESIGN REPORT [GDR] | 230 | 0570 | 15
3.230.05.70.20 | 1 | PAVEMENT DESIGN REPORT | 230 | 0570 | 20
3.230.05.70.25 | 1 | MATERIALS REPORT | 230 | 0570 | 25
3.230.05.99 | 1 | OTHER DRAFT ROADWAY PLAN PRODUCTS | 230 | 0599
3.230.10 | 1 | DRAFT HIGHWAY PLANTING PLANS | 230 | 10
3.230.10.05 | 1 | HIGHWAY PLANTING PLANS | 230 | 1005
3.230.10.15 | 1 | PLANT LIST | 230 | 1015
3.230.10.20 | 1 | IRRIGATION PLANS | 230 | 1020
3.230.10.30 | 1 | IRRIGATION QUANTITY SHEETS | 230 | 1030
3.230.10.99 | 1 | OTHER DRAFT ROADWAY PLAN PRODUCTS | 230 | 1099
3.230.15 | 1 | DRAFT TRAFFIC PLANS | 230 | 15
3.230.15.05 | 1 | SIGNING AND PAVEMENT DELINEATION PLANS | 230 | 1505
3.230.15.10 | 1 | CONSTRUCTION AREA SIGNS PLANS | 230 | 1510
3.230.15.15 | 1 | TRAFFIC ELECTRICAL PLANS | 230 | 1515
3.230.15.99 | 1 | OTHER DRAFT TRAFFIC PLAN PRODUCTS | 230 | 1599
3.230.20 | 1 | TRANSPORTATION MANAGEMENT PLAN | 230 | 20
3.230.25 | 1 | DRAFT UTILITY PLANS | 230 | 25
3.230.25.05 | 1 | NEW FACILITY PLANS | 230 | 2505
3.230.25.10 | 1 | UTILITY RELOCATION PLANS | 230 | 2510
3.230.25.99 | 1 | OTHER DRAFT UTILITY PLAN PRODUCTS | 230 | 2599
3.230.30 | 1 | DRAFT DRAINAGE PLANS | 230 | 30
3.230.35 | 1 | DRAFT SPECIFICATIONS | 230 | 35
3.230.35.05 | 1 | ROADWAY SPECIFICATIONS | 230 | 3505
3.230.35.10 | 1 | HIGHWAY PLANTING SPECIFICATIONS | 230 | 3510
3.230.35.15 | 1 | TRAFFIC SPECIFICATIONS | 230 | 3515
3.230.35.20 | 1 | ELECTRICAL SPECIFICATIONS | 230 | 3520
3.230.35.25 | 1 | UTILITY SPECIFICATIONS | 230 | 3525
3.230.35.30 | 1 | HYDRAULIC SPECIFICATIONS | 230 | 3530
3.230.35.35 | 1 | WATER POLLUTION CONTROL SPECIFICATIONS | 230 | 3535
3.230.35.40 | 1 | EROSION CONTROL SPECIFICATIONS | 230 | 3540
3.230.35.99 | 1 | OTHER DRAFT SPECIFICATION PRODUCTS | 230 | 3599
3.230.40 | 1 | DRAFT PS&E QUANTITIES AND ESTIMATES | 230 | 40
3.230.40.05 | 1 | ROADWAY QUANTITIES AND ESTIMATES | 230 | 4005
3.230.40.10 | 1 | HIGHWAY PLANTING QUANTITIES AND ESTIMATES | 230 | 4010
3.230.40.15 | 1 | DRAINAGE QUANTITIES AND ESTIMATES | 230 | 4015
3.230.40.20 | 1 | TRAFFIC QUANTITIES AND ESTIMATES | 230 | 4020
3.230.40.25 | 1 | ELECTRICAL QUANTITIES AND ESTIMATES | 230 | 4025
3.230.40.30 | 1 | UTILITY QUANTITIES AND ESTIMATES | 230 | 4030
3.230.40.35 | 1 | WATER POLLUTION CONTROL QUANTITIES AND ESTIMATES | 230 | 4035
3.230.40.40 | 1 | EROSION CONTROL QUANTITIES AND ESTIMATES | 230 | 4040
3.230.40.99 | 1 | OTHER DRAFT PS&E QUANTITIES AND ESTIMATES PRODUCTS | 230 | 4099
3.230.55 | 1 | STRUCTURES DRAFT PS&E INCORPORATION | 230 | 55
3.230.60 | 1 | UPDATED PROJECT INFORMATION FOR PS&E PACKAGE | 230 | 60
3.230.60.05 | 1 | UPDATED STORM WATER DATA REPORT | 230 | 6005
3.230.60.10 | 1 | OTHER REVIEWS AND UPDATE OF PROJECT INFORMATION | 230 | 6010
3.230.90 | 1 | NEPA DELEGATION | 230 | 90
3.230.99 | 1 | OTHER DRAFT PS&E PRODUCTS | 230 | 99
3.235 | 1 | MITIGATE ENVIRONMENTAL IMPACTS AND CLEAN-UP HAZARDOUS WASTE | 235
3.235.05 | 1 | ENVIRONMENTAL MITIGATION | 235 | 05
3.235.05.05 | 1 | HISTORICAL STRUCTURES MITIGATION | 235 | 0505
3.235.05.10 | 1 | ARCHAEOLOGICAL AND CULTURAL MITIGATION | 235 | 0510
3.235.05.15 | 1 | BIOLOGICAL MITIGATION | 235 | 0515
3.235.05.20 | 1 | ENVIRONMENTAL MITIGATION RIGHT OF WAY WORK | 235 | 0520
3.235.05.25 | 1 | PALEONTOLOGY MITIGATION | 235 | 0525
3.235.05.99 | 1 | OTHER ENVIRONMENTAL MITIGATION PRODUCTS | 235 | 0599
3.235.10 | 1 | DETAILED SITE INVESTIGATION FOR HAZARDOUS WASTE | 235 | 10
3.235.10.05 | 1 | RIGHT OR PERMIT FOR HAZARDOUS WASTE SITE INVESTIGATIONS [SI] | 235 | 1005
3.235.10.10 | 1 | HAZARDOUS WASTE SITES SURVEY | 235 | 1010
3.235.10.15 | 1 | DETAILED HAZARDOUS WASTE SITE INVESTIGATION SI | 235 | 1015
3.235.15 | 1 | HAZARDOUS WASTE MANAGEMENT PLAN | 235 | 15
3.235.20 | 1 | HAZARDOUS WASTE PS&E | 235 | 20
3.235.25 | 1 | HAZARDOUS WASTE CLEAN-UP | 235 | 25
3.235.30 | 1 | HAZARDOUS SUBSTANCES DISCLOSURE DOCUMENT [HSDD] | 235 | 30
3.235.35 | 1 | LONG TERM MITIGATION MONITORING | 235 | 35
3.235.40 | 1 | UPDATED ENVIRONMENTAL COMMITMENTS RECORD | 235 | 40
3.235.45 | 1 | NEPA DELEGATION | 235 | 45
3.240 | 1 | DRAFT STRUCTURES PS&E | 240
3.240.50 | 1 | OVERALL DRAFT STRUCTURES PS&E | 240 | 50
3.240.55 | 1 | FOUNDATION PLAN | 240 | 55
3.240.60 | 1 | HYDRAULICS REPORT | 240 | 60
3.240.65 | 1 | PRELIMINARY FOUNDATION REPORT | 240 | 65
3.240.70 | 1 | PRODUCTS REQUIRED TO READY SITE FOR SUBSURFACE EXPLORATION | 240 | 70
3.240.75 | 1 | DRAFT GENERAL PLANS | 240 | 75
3.240.80 | 1 | FOUNDATION REPORT | 240 | 80
3.240.85 | 1 | DRAFT STRUCTURE PLANS | 240 | 85
3.240.90 | 1 | DRAFT STRUCTURES SPECIAL PROVISIONS AND COST ESTIMATE | 240 | 90
3.250 | 1 | FINAL STRUCTURES PS&E PACKAGE | 250
3.250.50 | 1 | PROJECT REVIEW | 250 | 50
3.250.55 | 1 | FINAL STRUCTURE PLANS | 250 | 55
3.250.60 | 1 | FINAL STRUCTURE SPECIAL PROVISIONS AND COST ESTIMATE | 250 | 60
3.255 | 1 | CIRCULATE REVIEW AND PREPARE FINAL DISTRICT PS&E PACKAGE | 255
3.255.05 | 1 | CIRCULATED & REVIEWED DRAFT DISTRICT PS&E PACKAGE | 255 | 05
3.255.10 | 1 | UPDATED PS&E PACKAGE | 255 | 10
3.255.10.05 | 1 | UPDATED ROADWAY PS&E | 255 | 1005
3.255.10.10 | 1 | UPDATED HIGHWAY PLANTING PS&E | 255 | 1010
3.255.10.15 | 1 | UPDATED TRAFFIC PS&E | 255 | 1015
3.255.10.20 | 1 | UPDATED HYDRAULIC PS&E | 255 | 1020
3.255.10.25 | 1 | UPDATED TECHNICAL REPORTS | 255 | 1025
3.255.10.30 | 1 | UPDATED UTILITY PS&E | 255 | 1030
3.255.10.35 | 1 | UPDATED ELECTRICAL PS&E | 255 | 1035
3.255.10.99 | 1 | OTHER UPDATED PS&E PACKAGE PRODUCTS | 255 | 1099
3.255.15 | 1 | ENVIRONMENTAL REEVALUATION | 255 | 15
3.255.20 | 1 | FINAL DISTRICT PS&E PACKAGE | 255 | 20
3.255.20.05 | 1 | REVIEWED PLANS FOR DRAFTING STANDARDS COMPLIANCE | 255 | 2005
3.255.20.10 | 1 | FINAL STRUCTURES SPECIFICATIONS AND ESTIMATE INCORPORATED INTO FINAL DISTRICT PS&E | 255 | 2010
3.255.20.15 | 1 | REQUEST FOR FUNDS | 255 | 2015
3.255.25 | 1 | GEOTECHNICAL INFORMATION HANDOUT | 255 | 25
3.255.30 | 1 | MATERIALS INFORMATION HANDOUT | 255 | 30
3.255.35 | 1 | CONSTRUCTION STAKING PACKAGE AND CONTROL | 255 | 35
3.255.35.10 | 1 | CONSTRUCTION STAKING PACKAGE | 255 | 3510
3.255.35.20 | 1 | PROJECT CONTROL FOR CONSTRUCTION | 255 | 3520
3.255.40 | 1 | RESIDENT ENGINEER'S PENDING FILE | 255 | 40
3.255.45 | 1 | NEPA DELEGATION | 255 | 45
3.255.50 | 1 | SECURED LEASE FOR RESIDENT ENGINEER OFFICE SPACE OR TRAILER | 255 | 50
3.255.55 | 1 | CONTRACTOR OUTREACH | 255 | 55
3.255.65 | 1 | RIGHT OF WAY CERTIFICATION DOCUMENT | 255 | 65
3.255.70 | 1 | RIGHT OF WAY ENGINEERING PRODUCTS | 255 | 70
3.255.75 | 1 | UPGRADED/UPDATED RIGHT OF WAY CERTIFICATION DOCUMENT | 255 | 75
3.260 | 1 | CONTRACT BID DOCUMENTS “READY TO LIST” | 260
3.260.50 | 1 | PROJECT SUBMITTAL READY TO PROCESS [PS&E] | 260 | 50
3.260.60 | 1 | DRAFT CONTRACT COMMENTS [DCC] | 260 | 60
3.260.70 | 1 | DRAFT CONTRACT COMMENT RESPONSE [DR] | 260 | 70
3.260.75 | 1 | ENVIRONMENTAL CERTIFICATION AT RTL | 260 | 75
3.260.80 | 1 | DRAFT CONTRACT READY | 260 | 80
3.260.90 | 1 | READY TO LIST [RTL] | 260 | 90
3.265 | 1 | AWARDED AND APPROVED CONSTRUCTION CONTRACT | 265
3.265.50 | 1 | CONTRACT READY FOR ADVERTISING | 265 | 50
3.265.55 | 1 | ADVERTISED CONTRACT | 265 | 55
3.265.60 | 1 | BIDS OPENED | 265 | 60
3.265.65 | 1 | CONTRACT AWARD | 265 | 65
3.265.70 | 1 | EXECUTED AND APPROVED CONTRACT | 265 | 70
3.265.75 | 1 | INDEPENDENT ASSURANCE | 265 | 75
4.195 | 2 | RIGHT OF WAY PROPERTY MANAGEMENT AND EXCESS LAND | 195
4.195.40 | 2 | PROPERTY MANAGEMENT | 195 | 40
4.195.40.05 | 2 | FAIR MARKET RENT DETERMINATIONS [RESIDENTIAL] | 195 | 4005
4.195.40.10 | 2 | FAIR MARKET RENT DETERMINATIONS [NON-RESIDENTIAL] | 195 | 4010
4.195.40.15 | 2 | REGULAR PROPERTY MANAGEMENT | 195 | 4015
4.195.40.20 | 2 | PROPERTY MAINTENANCE AND REHABILITATION [RENTABLE PROPERTY] | 195 | 4020
4.195.40.25 | 2 | PROPERTY MAINTENANCE AND REHABILITATION [NON-RENTABLE PROPERTY] | 195 | 4025
4.195.40.30 | 2 | HAZARDOUS WASTE AND HAZARDOUS MATERIALS | 195 | 4030
4.195.40.35 | 2 | TRANSFER OF PROPERTY TO CLEARANCE STATUS | 195 | 4035
4.195.40.99 | 2 | OTHER PROPERTY MANAGEMENT PRODUCTS | 195 | 4099
4.195.45 | 2 | EXCESS LAND | 195 | 45
4.195.45.05 | 2 | EXCESS LANDS INVENTORY | 195 | 4505
4.195.45.10 | 2 | EXCESS LAND APPRAISAL AND PUBLIC SALE ESTIMATE | 195 | 4510
4.195.45.15 | 2 | GOVERNMENT CODE SECTION 54235 ADMINISTRATION | 195 | 4515
4.195.45.20 | 2 | PROPERTY DISPOSAL OF UNITS UP TO $15000 | 195 | 4520
4.195.45.25 | 2 | PROPERTY DISPOSAL OF UNITS BETWEEN $15001 AND $500000 | 195 | 4525
4.195.45.30 | 2 | PROPERTY DISPOSAL OF UNITS OVER $500000 | 195 | 4530
4.195.45.35 | 2 | CTC AND AAC COORDINATION | 195 | 4535
4.195.45.99 | 2 | OTHER EXCESS LAND PRODUCTS | 195 | 4599
4.200 | 2 | UTILITY RELOCATION | 200
4.200.15 | 2 | APPROVED UTILITY RELOCATION PLAN | 200 | 15
4.200.20 | 2 | UTILITY RELOCATION PACKAGE | 200 | 20
4.200.25 | 2 | UTILITY RELOCATION MANAGEMENT | 200 | 25
4.200.30 | 2 | UTILITY CLOSE OUT | 200 | 30
4.200.99 | 2 | OTHER UTILITY RELOCATION PRODUCTS | 200 | 99
4.220 | 2 | RIGHT OF WAY ENGINEERING | 220
4.220.05 | 2 | EXISTING LAND NET | 220 | 05
4.220.05.05 | 2 | EXISTING RECORDS | 220 | 0505
4.220.05.10 | 2 | LAND NET SURVEY | 220 | 0510
4.220.05.25 | 2 | MONUMENTATION PERPETUATION RECORD OF SURVEY | 220 | 0525
4.220.10 | 2 | LAND NET MAP | 220 | 10
4.220.15 | 2 | RIGHT OF WAY MAPS | 220 | 15
4.220.15.05 | 2 | APPRAISAL MAPS | 220 | 1505
4.220.15.95 | 2 | OTHER MAPS | 220 | 1595
4.220.20 | 2 | ACQUISITION DOCUMENTS | 220 | 20
4.220.20.05 | 2 | DEEDS | 220 | 2005
4.220.20.15 | 2 | RESOLUTION OF NECESSITY PACKAGE | 220 | 2015
4.220.25 | 2 | DOCUMENTS TO CONVEY PROPERTY RIGHTS | 220 | 25
4.220.25.05 | 2 | DIRECTOR'S DEED PACKAGE | 220 | 2505
4.220.25.95 | 2 | OTHER DEEDS AND DOCUMENTS | 220 | 2595
4.220.35 | 2 | FIELD LOCATED RIGHT OF WAY | 220 | 35
4.220.35.05 | 2 | FLAGGED RIGHT OF WAY | 220 | 3505
4.220.35.10 | 2 | STAKED RIGHT OF WAY | 220 | 3510
4.225 | 2 | OBTAIN RIGHT OF WAY INTERESTS FOR PROJECT RIGHT OF WAY CERTIFICATION | 225
4.225.50 | 2 | PARCEL AND PROJECT DOCUMENTATION | 225 | 50
4.225.60 | 2 | RIGHT OF WAY APPRAISALS | 225 | 60
4.225.65 | 2 | RIGHT OF WAY ACQUISITION | 225 | 65
4.225.70 | 2 | RIGHT OF WAY RELOCATION ASSISTANCE | 225 | 70
4.225.75 | 2 | RIGHT OF WAY CLEARANCE | 225 | 75
4.225.80 | 2 | RIGHT OF WAY CONDEMNATION | 225 | 80
4.245 | 2 | POST RIGHT OF WAY CERTIFICATION WORK | 245
4.245.50 | 2 | PARCEL AND PROJECT DOCUMENTATION | 245 | 50
4.245.60 | 2 | RIGHT OF WAY APPRAISALS | 245 | 60
4.245.65 | 2 | RIGHT OF WAY ACQUISITION | 245 | 65
4.245.70 | 2 | RIGHT OF WAY RELOCATION ASSISTANCE | 245 | 70
4.245.75 | 2 | RIGHT OF WAY CLEARANCE | 245 | 75
4.245.80 | 2 | RIGHT OF WAY CONDEMNATION | 245 | 80
4.300 | 2 | FINAL RIGHT OF WAY ENGINEERING | 300
4.300.05 | 2 | RIGHT OF WAY MONUMENTATION | 300 | 05
4.300.05.05 | 2 | RIGHT OF WAY MONUMENTATION SURVEY | 300 | 0505
4.300.05.10 | 2 | FILED MONUMENTATION RECORD OF SURVEY | 300 | 0510
4.300.10 | 2 | TRIAL EXHIBITS AND TESTIMONY | 300 | 10
4.300.25 | 2 | RELINQUISHMENT AND VACATION MAPS | 300 | 25
4.300.30 | 2 | DEED PACKAGE FOR EXCESS LAND TRANSACTIONS | 300 | 30
4.300.35 | 2 | RIGHT OF WAY RECORD MAP | 300 | 35
5.270 | 3 | CONSTRUCTION ENGINEERING AND GENERAL CONTRACT ADMINISTRATION | 270
5.270.10 | 3 | CONSTRUCTION STAKING PACKAGE AND CONTROL | 270 | 10
5.270.10.10 | 3 | CONSTRUCTION STAKING PACKAGE | 270 | 1010
5.270.10.20 | 3 | PROJECT CONTROL FOR CONSTRUCTION | 270 | 1020
5.270.15 | 3 | CONSTRUCTION STAKES | 270 | 15
5.270.15.15 | 3 | SLOPE STAKES | 270 | 1515
5.270.15.25 | 3 | ROUGH GRADE STAKES | 270 | 1525
5.270.15.30 | 3 | FINAL GRADE STAKES | 270 | 1530
5.270.15.35 | 3 | DRAINAGE AND MINOR STRUCTURE STAKES | 270 | 1535
5.270.15.50 | 3 | MISCELLANEOUS STAKES | 270 | 1550
5.270.15.55 | 3 | PHOTOGRAMMETRIC PRODUCT FOR CONSTRUCTION | 270 | 1555
5.270.15.60 | 3 | GROUND STAKES FOR MAJOR STRUCTURE | 270 | 1560
5.270.15.65 | 3 | SUPERSTRUCTURE STAKES FOR MAJOR STRUCTURE | 270 | 1565
5.270.20 | 3 | CONSTRUCTION ENGINEERING WORK | 270 | 20
5.270.20.05 | 3 | RESIDENT ENGINEER'S FILE REVIEW | 270 | 2005
5.270.20.10 | 3 | PROJECT PLANS SPECIAL PROVISIONS AND ESTIMATE REVIEW | 270 | 2010
5.270.20.15 | 3 | CONTRACT PAY QUANTITIES | 270 | 2015
5.270.20.20 | 3 | LINES AND GRADES CONTROL | 270 | 2020
5.270.20.25 | 3 | CONTRACTORS' FALSEWORK SUBMITTALS REVIEW | 270 | 2025
5.270.20.30 | 3 | CONTRACTORS' TRENCHING AND SHORING SUBMITTALS REVIEW | 270 | 2030
5.270.20.35 | 3 | SHOP PLANS REVIEW | 270 | 2035
5.270.20.40 | 3 | COST REDUCTION INCENTIVE PROPOSALS [CRIPS] REVIEW | 270 | 2040
5.270.20.45 | 3 | CONTRACTORS' WATER POLLUTION CONTROL PROGRAM REVIEW | 270 | 2045
5.270.20.50 | 3 | TECHNICAL SUPPORT | 270 | 2050
5.270.20.99 | 3 | OTHER CONSTRUCTION ENGINEERING WORK PRODUCTS | 270 | 2099
5.270.25 | 3 | CONSTRUCTION CONTRACT ADMINISTRATION WORK | 270 | 25
5.270.25.05 | 3 | SECURED LEASE FOR RESIDENT ENGINEER OFFICE SPACE OR TRAILER | 270 | 2505
5.270.25.10 | 3 | SET UP CONSTRUCTION PROJECT FILES | 270 | 2510
5.270.25.15 | 3 | PRE-CONSTRUCTION MEETING | 270 | 2515
5.270.25.20 | 3 | PROGRESS PAY ESTIMATES | 270 | 2520
5.270.25.25 | 3 | WEEKLY STATEMENT OF WORKING DAYS | 270 | 2525
5.270.25.30 | 3 | CONSTRUCTION PROJECT FILES AND GENERAL FIELD OFFICE CLERICAL WORK | 270 | 2530
5.270.25.35 | 3 | LABOR COMPLIANCE ACTIVITIES | 270 | 2535
5.270.25.40 | 3 | APPROVED SUBCONTRACTOR SUBSTITUTIONS | 270 | 2540
5.270.25.45 | 3 | COORDINATION | 270 | 2545
5.270.25.50 | 3 | CIVIL RIGHTS CONTRACT COMPLIANCE | 270 | 2550
5.270.25.99 | 3 | OTHER CONSTRUCTION CONTRACT ADMINISTRATION WORK PRODUCTS | 270 | 2599
5.270.30 | 3 | CONTRACT ITEM WORK INSPECTION | 270 | 30
5.270.30.05 | 3 | PHOTOGRAPHED JOBSITE AND CONTRACTORS' OPERATIONS | 270 | 3005
5.270.30.10 | 3 | INSPECTION OF CONTRACTORS' WORK FOR COMPLIANCE | 270 | 3010
5.270.30.15 | 3 | CONTRACTORS' OPERATIONS RELATIVE TO SAFETY REQUIREMENTS DOCUMENTATION | 270 | 3015
5.270.30.20 | 3 | DAILY DIARY OF CONTRACT OPERATIONS | 270 | 3020
5.270.30.25 | 3 | PUNCH LIST | 270 | 3025
5.270.35 | 3 | CONSTRUCTION MATERIAL SAMPLING AND TESTING | 270 | 35
5.270.35.05 | 3 | MATERIALS SAMPLING AND TESTING FOR QUALITY ASSURANCE | 270 | 3505
5.270.35.10 | 3 | PLANT INSPECTION FOR QUALITY ASSURANCE | 270 | 3510
5.270.35.15 | 3 | INDEPENDENT ASSURANCE SAMPLING AND TESTING | 270 | 3515
5.270.35.20 | 3 | SOURCE INSPECTION | 270 | 3520
5.270.40 | 3 | SAFETY AND MAINTENANCE REVIEWS | 270 | 40
5.270.45 | 3 | RELIEF FROM MAINTENANCE PROCESS | 270 | 45
5.270.55 | 3 | FINAL INSPECTION AND ACCEPTANCE RECOMMENDATION | 270 | 55
5.270.60 | 3 | PLANT ESTABLISHMENT ADMINISTRATION | 270 | 60
5.270.65 | 3 | TMP IMPLEMENTATION DURING CONSTRUCTION | 270 | 65
5.270.70 | 3 | UPDATED ENVIRONMENTAL COMMITMENTS RECORD | 270 | 70
5.270.75 | 3 | RESOURCE AGENCY PERMIT RENEWAL AND EXTENSION REQUESTS | 270 | 75
5.270.80 | 3 | LONG-TERM ENVIRONMENTAL MITIGATION/MITIGATION MONITORING DURING CONSTRUCTION CONTRACT | 270 | 80
5.270.99 | 3 | OTHER CONSTRUCTION ENGINEERING AND GENERAL CONTRACT ADMINISTRATION | 270 | 99
5.275 | 3 | CONSTRUCTION ENGINEERING AND GENERAL CONTRACT ADMINISTRATION OF STRUCTURES WORK | 275
5.275.10 | 3 | OFFICE ADMINISTRATION WORK FOR STRUCTURES | 275 | 10
5.275.20 | 3 | FIELD ADMINISTRATION WORK FOR STRUCTURES | 275 | 20
5.275.30 | 3 | CONTRACT CHANGE ORDER INSPECTION FOR STRUCTURES WORK | 275 | 30
5.275.40 | 3 | SAFETY TASKS FOR STRUCTURES WORK | 275 | 40
5.285 | 3 | CONTRACT CHANGE ORDER ADMINISTRATION | 285
5.285.05 | 3 | CONTRACT CHANGE ORDER [CCO] PROCESS | 285 | 05
5.285.05.05 | 3 | NEED FOR CCO DETERMINATION | 285 | 0505
5.285.05.10 | 3 | DRAFT CONTRACT CHANGE ORDER | 285 | 0510
5.285.05.15 | 3 | CONTRACT CHANGE ORDER APPROVAL | 285 | 0515
5.285.05.20 | 3 | PAYMENTS FOR CONTRACT CHANGE ORDER WORK | 285 | 0520
5.285.10 | 3 | FUNCTIONAL SUPPORT | 285 | 10
5.285.10.05 | 3 | FIELD SURVEYS FOR CONTRACT CHANGE ORDER | 285 | 1005
5.285.10.10 | 3 | STAKING FOR CONTRACT CHANGE ORDER | 285 | 1010
5.285.10.15 | 3 | OTHER FUNCTIONAL SUPPORT | 285 | 1015
5.290 | 3 | RESOLVE CONTRACT CLAIMS | 290
5.290.05 | 3 | ANALYSIS OF NOTICES OF POTENTIAL CLAIMS | 290 | 05
5.290.10 | 3 | SUPPORTING DOCUMENTATION AND RESPONSES TO NOTICES OF POTENTIAL CLAIMS | 290 | 10
5.290.15 | 3 | REVIEWED AND APPROVED CLAIM REPORT | 290 | 15
5.290.20 | 3 | DISTRICT CLAIM MEETING OR BOARD OF REVIEW | 290 | 20
5.290.25 | 3 | ARBITRATION HEARING | 290 | 25
5.290.30 | 3 | NEGOTIATED CLAIM SETTLEMENT | 290 | 30
5.290.35 | 3 | TECHNICAL SUPPORT | 290 | 35
5.295 | 3 | ACCEPT CONTRACT/ PREPARE FINAL CONSTRUCTION ESTIMATE AND FINAL REPORT | 295
5.295.05 | 3 | PROCESSED ESTIMATE AFTER ACCEPTANCE | 295 | 05
5.295.10 | 3 | PROPOSED FINAL CONTRACT ESTIMATE | 295 | 10
5.295.15 | 3 | AS-BUILT PLANS | 295 | 15
5.295.20 | 3 | PROJECT HISTORY FILE | 295 | 20
5.295.25 | 3 | FINAL REPORT | 295 | 25
5.295.30 | 3 | PROCESSED FINAL ESTIMATE | 295 | 30
5.295.35 | 3 | CERTIFICATE OF ENVIRONMENTAL COMPLIANCE | 295 | 35
5.295.40 | 3 | LONG TERM ENVIRONMENTAL MITIGATION/MITIGATION MONITORING AFTER CONSTRUCTION CONTRACT ACCEPTANCE | 295 | 40
5.295.45 | 3 | POST-CONSTRUCTION TRAFFIC OPERATIONS ACTIVITIES | 295 | 45
5.295.45.05 | 3 | SPEED SURVEY RECORDS | 295 | 4505
5.295.45.05.05 | 3 | SPEED SURVEY | 295 | 4505 | 05
5.295.45.05.10 | 3 | SIGNED SPEED SURVEY | 295 | 4505 | 10
5.295.45.10 | 3 | COMMISSION TMS ELEMENTS | 295 | 4510
5.295.99 | 3 | OTHER ACCEPT CONTRACT/ PREPARE FINAL CONSTRUCTION ESTIMATE AND FINAL REPORT | 295 | 99